LETTER OF AGREEMENT 105/2025

Between

The Food and Agriculture Organization of the United Nations (“FAO”)

And the

Tanzania Fisheries Research Institute (TAFIRI)

For Provision of

Implementation of Fisheries Stock Assessment Training, Strategy Development and Study Tour under the TCP program (TCP/SOM/4003)

1st Progress Report

| Service Provider | Tanzania Fisheries Research Institute) | Reporting Period |  | From: | To: |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | 10th December 2025 | 10th March 2026 |
| Area of intervention | Region/s |  | District/s |  |  |
|  | TANZANIA |  | Dar es Salam |  |  |

Report prepared by:

Fisheries Stock Assessment Experts (Dr. Ismael Kimirei, Dr. Rushingisha George, Dr. Masumbuko Semba, & Dr. Mary Kishe)

Tanzania Fisheries Research Institute

# Table of contents

Executive Summary	3

1.	Objectives and Outcomes achieved	5

2.	Project Implementation	10

3.	Other Activities implemented.	10

4.	Problems encountered	10

5.	COVID-19 prevention and control measures	10

6.	Commitments on Accountability to Affected Population (AAP) Session	10

7.	Prevention of Sexual exploitation and Abuse (PSEA)	11

8.	Recommendations	11

9.	Lessons learned	11

10.	Photographic evidence of work completed	11

# Executive Summary

Fisheries are a cornerstone of food security, livelihoods, and the blue economy in Somalia, making sustainable management of these resources a national priority. In recognition of the critical role that robust scientific data and information play in effective fisheries management, FAO Somalia (FAOSO) is supporting the Ministry of Fisheries and Blue Economy to strengthen national capacity in fish stock assessment.

On 10th December 2025, the Tanzania Fisheries Research Institute (TAFIRI), in partnership with the Food and Agriculture Organization of the United Nations (FAO), signed a Letter of Agreement (Letter of Agreement (LoA# 105/2025) for the provision of services on the implementation of fisheries stock assessment training, strategy development, and a study tour under the TCP programme (TCP/SOM/4003).

TAFIRI has successfully conducted Activity 1 of the LoA—Project Team Nomination and Briefing—during which five experts were nominated on 10th December 2025 to implement the project activities in accordance with the project work plan.

Following completion of Activity 1, the project team then implemented Activity 2—Training Needs Assessment (TNA). The main objective of the TNA was to evaluate the participants’ capacity and baseline understanding of key aspects of fish stock assessment. Preparatory work for the TNA—including a literature review and designing of a semi-structured interviews using a questionnaire, as well as a virtual meeting to discuss self-assessment results and agree on training priorities and delivery modes—were carried out between 3rd and 7th December 2025. On 5th December 2025, TAFIRI shared an online questionnaire for participants to complete ahead of a virtual session held on 6th December 2025 from 14:00 to 16:00 hours, which aimed at validating the results of the TNA and collecting extra information that could not be captured in the online questionnaire. During the virtual session, the team presented the TNA findings and discussed priority areas of focus, training modules, curriculum, and the preferred mode of delivery.

After completing Activity 2, the project team proceeded with Activity 3, which was to Prepare detailed training objectives, training plan, modules, and materials for all participants. The objective of this activity was to develop training modules on stock assessment, a detailed course plan, and all necessary training materials. The team prepared all key documents during 7–8 December 2025 and shared them with FAOSO for review and approval on 9 December 2025. The draft manuals covered, among others: fundamental concepts in fish stock assessment; sampling and data collection; data organization and processing; and data analysis and reporting.

To be continued based on activity completion…..

# Objectives and Outcomes achieved

To strengthen national fisheries management capacity in Somalia by delivering an integrated programme comprising stock assessment training, a regional study tour, and hands-on learning at landing sites and aboard a fishing-cum-research vessel through TAFIRI. The goal was to enhance the capacity of the Ministry of Fisheries and Blue Economy of Somalia to collect, analyse, and interpret fisheries data for evidence-based decision-making, while supporting the development and effective use of a Fisheries Information Management System (FIMS). Ultimately, this will be achieved through a coordinated approach to promoting sustainable, science-based fisheries management in Somalia.

| Project activity targets as per the LoA | Actual achievements up to the date of reporting | Remarks (Actions/Recommendations) |  |
| --- | --- | --- | --- |
| Activity 1: Project team nomination and briefing | On 10th December 2025, following the signature of the LoA between the two counterparts, TAFIRI management nominated four fish stock assessment experts and a project manager (Table 1) to facilitate the implementation of the project. Immediately after the nomination, TAFIRI and FAO conducted a joint briefing session to facilitate effective and timely execution of the planned activities. Table 1: Nominated fish stock assessment experts. Name; Title; Task; Email and mobile phone. Dr. Ismael Kimirei; Lead consultant; Lead Fisheries Scientist / Team Leader (Preparation, Training & Mentorship); dg@tafiri.go.tz; +255786451468. Dr Rushingisha George; Consultant; Report Writing and documentation expert; george.rushingisha@tafiri.go.tz; +255713277006. Dr Masumbuko Semba; Consultant; Fisheries Data & Modelling Expert; masumbukosemba@nm-aist.ac.tz; +255717603703. Dr Mary Kishe; Consultant; Training Specialist / Co-Trainer / Strategy Developer (desk review & drafting Somali stock assessment strategy); mary.kishe@tafiri.go.tz; +255784317539. Ms Edith Kambo; Consultant; Project manager; edith.kambo@tafiri.go.tz; +255763100619. Nominated TAFIRI staff assigned to the LoA activities criteria is attached as (Annex 1) | Com pleted |  |
| Activity 2: Conduct Training Need Assessment | Introduction: Effective capacity building in fish stock assessment requires a clear understanding of existing staff competencies, practical experience, and institutional gaps. In this regard, conducting a Training Needs Assessment (TNA) is a critical prerequisite to the design of any specialized training course, as it ensures that training modules are context-specific, demand-driven, and directly responsive to participants’ needs. Ahead of the planned 10-day stock assessment training, a Training Needs Assessment (TNA) was carried out from 3–7 December 2025 using a structured three-stage approach. First, the team of experts reviewed the Capacity Assessment Report prepared by Diress in 2024 to gain an understanding of the context of the fisheries in Somalia, including key constraints and opportunities. This task was undertaken at the TAFIRI offices in Dar es Salaam. Second, the selected trainees completed an online questionnaire (https://ee.kobotoolbox.org/x/BXiGe9in), which was administered through the Kobo Tool between 5 and 6 December 2025, thus providing self-assessments of the participants’ technical competencies, practical experience, and training preferences. Third, on 6th December 2025, the preliminary self-assessment results were presented (https://lugoga.github.io/stock_training_somalia/presentations/tna_presentation.html#/title-slide) and discussed with participants during a virtual meeting held from 14:00 to 16:00 hours (https://teams.microsoft.com/v2/), organized by FAOSO. This interactive session enabled the team of experts to validate, refine, and enrich the TNA findings, thereby ensuring that the final training modules are closely aligned with the Somali context. Participants included representatives from key government institutions and organizations, notably the Ministry of Fisheries and the Blue Economy. Data: The assessment relied on participants’ self-reported information to identify gaps in their existing skills and knowledge. Number of participants: A total of twelve participants took part in the TNA. Although the Terms of Reference (TOR) had initially indicated sixteen participants, four were unable to participate due to unforeseen circumstances. Objectives: To gain an understanding of existing staff competencies, practical experience, and institutional gaps in fish stock assessment capacity in Somalia. Findings: Somalia has not conducted a formal fish stock assessment since 1991, largely due to limited technical capacity. Although most prospective trainees hold educational backgrounds in fisheries or marine science, self-assessment results indicate that the majority possess only basic to intermediate skills necessary for conducting stock assessments. Based on participants’ feedback, the training priorities were refined to emphasize key stock assessment concepts, standardized data collection protocols, and appropriate analytical methods, with particular attention to approaches suited to data-poor fisheries. A significant capacity gap was identified in the collection of biological data—especially fecundity estimation and determination of fish maturity stages. In addition, all participants reported limited proficiency in software used for analyzing large datasets, such as the R programming language, relying instead almost exclusively on Excel, which is inadequate for implementing fisheries stock assessment models such as Length-based Spawning Potential Ratio (LBSPR). Participants further highlighted the need for increased time allocation to practical, hands-on training sessions instead of classroom-type theoretical presentations. Outcomes: The TNA results were instrumental in developing stock assessment training course specifically tailored to the Somali fisheries context. This included not only the creation of relevant modules but also a plan for course delivery and the identification of all necessary training materials. Conclusions: Staff of the Ministry of Fisheries and Blue Economy currently have limited capacity to independently undertake fish stock assessments. The TNA clearly identified priority areas for strengthening this capacity and provides a strong evidence base for the design of targeted interventions. Thus, the development of training modules should be carefully aligned with participants’ existing skill levels, as well as with the practical and technical constraints and opportunities presented by the fisheries data available in Somalia. Moreover, the strong preference for practical, hands-on learning highlights the importance of an applied and context-specific curriculum that enables participants to effectively translate theoretical concepts into practice using real-world Somali fisheries data and management scenarios. Recommendations: It is recommended that: (1) To maximize relevance and practical value, participants should bring their own datasets, allowing training activities to be directly connected to their daily work and providing hands-on experience in applying stock assessment methodologies. (2) Participants are encouraged to bring their own fisheries datasets to the training. Engaging with real data from their daily responsibilities will enhance the relevance and practicality of the exercises, improve problem-solving skills, and enable the immediate application of newly acquired knowledge within their institutional roles. A detailed report of the meetings is attached separately as annex 2. | Successfully completed |  |
| Activity 3: Prepare detailed training objectives, training plan, modules, and materials for all participants. | Introduction: The TNA revealed that most trainees hold advanced degrees in fisheries-related fields, with their knowledge of fish stock assessment generally spanning from basic to intermediate levels. Participants expressed a strong preference for practical, application-oriented training, emphasizing the importance of robust data collection methodologies and comprehensive data analysis supported by hands-on exercises. The training module was developed based on the results of the TNA. The course will be delivered through a blended approach, combining lectures, computer-based practical exercises, group work and discussions, as well as field-based activities at landing sites and during a ship-based survey. Data: The training demonstrations will draw upon length-weight data of fish originating from artisanal fisheries in Somalia, with additional data sourced from artisanal and industrial fisheries in Tanzania, which will be provided by TAFIRI. Number of participants: A total of twelve participants took part in the TNA. Although the ToR had initially indicated sixteen participants, four were unable to participate due to unforeseen circumstances Objectives: To develop modules for the stock assessment training, a detailed course plan, and all necessary materials for the stock assessment training. Findings: Based on the results of the TNA, a training course was developed consisting of five modules (Annex 3). The same document, also, includes a detailed delivery plan for each module and all necessary training materials. Outcomes: By the end of this training, participants will have developed a solid foundation to undertake fish stock assessment. Specifically, they will be able to: - Understand core principles: Explain the fundamental concepts of population dynamics and stock assessment, including key biological and ecological principles. - Design data collection: Identify and select appropriate sampling designs and survey types for effective fishery data collection in both artisanal and industrial contexts. - Understand data types and reference points: Demonstrate a clear understanding of various fisheries data types—catch, effort, biological, and environmental data—and apply biological and exploitation reference points (indices) relevant to fisheries assessment and management. - Apply practical skills: Collect length, weight, and gonad data using standardized field methods, and analyze these data using appropriate statistical and modeling tools. - Evaluate and interpret results: Critically assess the uncertainty, assumptions, and limitations inherent in fish stock assessment in Somalia and the wider Westen Indian Ocean region. - Communicate findings: Prepare and present simple stock assessment reports for selected species, applying the knowledge and skills gained to real-world fisheries management challenges in Somalia. Conclusions: The five training modules for the fish stock assessment course were designed based on the TNA and are tailored to the local needs of the participants. Despite being comprehensive, they can feasibly be delivered within the planned 10-day stock assessment training course. Recommendations: It is recommended that the training modules should be delivered in an adaptive manner, allowing the content and methods to be adjusted to suit participants’ needs and progress; and post the content online for future access and learning The document detailing the fish stock assessment training modules, delivery plan, and required materials is attached separate as annex 3. | Successfully completed |  |
| Activity 4: Deliver agreed on-land training program in Tanzania Fisheries Research Institute Der Salam Tanzania Over period of 7 days. | Not Done | On going |  |
| Activity 5: Conduct a research exercise aboard a research vessel, including hands-on data collection and observation of scientific survey operations. | Not Done | On going |  |
| Activity 6: Completion and Submission of the National Fisheries Stock Assessment Strategy by TAFIRI | Note done | Ongoing |  |

# Project Implementation

# Other Activities implemented.

Activity 1:

Activity 2:

Activity 3;

Other project activities

# Problems encountered

- The main challenge encountered related to the issuance of visas for participants, which were granted at different times, with some participants obtaining visas on arrival in Tanzania. TAFIRI ensured that all participants ultimately received their visas and could attend the course uninterrupted.

- The delay in advance payments posed a challenge to project implementation, as several service providers required upfront payment before delivering their services.

# COVID-19 prevention and control measures

The project team completed a training session for workshop participants to learn how to prevent and mitigate covid 19 at workplace and other places. Also, they have gained some information related to transmission of SARS-CoV-2, the virus that causes COVID-19, which has occurred in a wide range of workplaces outside of healthcare facilities. Participants learnt Policies aimed at protecting workers to help prevent community transmission of the virus and protect national economies by maintaining open and safe workplaces.

# Commitments on Accountability to Affected Population (AAP) Session

Throughout the workshop period, the project staff held a session that focused on the commitments to the affected population.

The trainees received hints and were taught about the AAP Policy on Age, Gender, and Diversity (AGD, 2018), specifically core actions 2-5:

- Participation and inclusion (Core Action 2).

- Communication and transparency (Core Action 3).

- Feedback and response (Core Action 4).

- Organizational learning and adaptation (Core Action 5).

# Prevention of Sexual exploitation and Abuse (PSEA)

The event participants were received a training session which concerned about  PSEA policies and practices, they were familiar with the  aim PSEA to reduce the risk of, prevent and respond to SEA by UN personnel, NGO partners, or other entities and persons involved in providing humanitarian or development assistance, including government staff, contractors, and community volunteers and workers, to ensure that allegations of SEA are reported and responded to in a timely and appropriate manner, and that victims of SEA are referred to support and assistance needed in line with a victim centered approach

# Recommendations

The following recommendations were forwarded:

Activity 1:

- (1) To maximize learning and skill transfer, a greater portion of training time should be devoted to practical, hands-on sessions. This will better reflect participants’ strong preference for applied learning over purely theoretical content and ensure that trainees gain direct experience in implementing stock assessment methodologies.

- (2) Course participants are encouraged to bring their own fisheries datasets to the training. Working directly with real data from their day-to-day responsibilities will increase the relevance and practicality of the exercises, strengthen problem-solving skills, and facilitate the immediate application of newly acquired knowledge in their institutional contexts.

Activity 2:

- The training modules should be delivered in an adaptive manner, allowing the content and methods to be adjusted to suit participants’ needs and progress.

Activity 3:

- Given that only ten days are allocated for the planned fish stock assessment training, the duration is too short for participants to become fully competent in conducting stock assessments. The course will provide participants with a basic understanding in stock assessment, covering key concepts, data types, collection methods, analysis, and interpretation. It is strongly recommended that this initial training be followed by continuous capacity development, including regular refresher courses, on-the-job mentoring, and practical exercises. In particular, establishing a dedicated capacity-building program that leverages South–South cooperation would be highly beneficial for sustaining and strengthening national expertise in fish stock assessment.

- Course materials should be deposited online to allow ease access and self-learning

# Lessons learned

- For future visits, TAFIRI will apply for a group visa for all participants to receive their visa on arrival, rather than having each participant apply individually for an online visa.

# Photographic evidence of work completed

Photos from the event can be accessed via the following Google Drive link: https://drive.google.com/drive/folders/1zEIZCy4GiUm7ex3_cumh9iU1pN9NqkoA

Annex II: Participant details

Annex III: Training Manuals (PPTs, Reference documents and technical teaching notes)

The training manuals and presentations can be accessed at the following link: https://lugoga.github.io/stock_training_somalia/